Agenda:
Alvechurch Parish Neighbourhood Plan 


Steering Group Meeting No.10

Date:

Thursday September 20th 2012
Venue:
Hopwood community Hall 10 am.

[image: image1.jpg]Alvechurch Parish

neighbourhood plan



Attended: Adrian Smith, Mary Green, Linda Allen, Dorothy Snaddon, Tom Thurrell, Sally Meredith (Lounge), Patrick Riley, Susan Whitehand (Barnt Green PC)

Apologies: Andy Humphries, Rick Chima
Minutes: The minutes of the August meeting were accepted. All matters arising appear on the agenda.
1. Review Gantt chart/project brief: Mary agreed to update the chart after this meeting to include base-line work
2. Finance report: Tom reported that from our budget of £250 we have £221.71 remaining. It was agreed to request £500 for next financial year.

3. New funding and CPRE response to training: There is as yet no response from our trainer to our assigned work after the training. CPRE have funding for the period up to April 2013, and we can apply for specific aspects. Adrian suggested SA training but will email round for other suggestions. BDC will have access to funding to support us, but this is for their expenses not ours…  
4. Group members’ projects on baseline information: papers have been circulated from Mary (environment) Dorothy (heritage) Adrian (housing) and John (business). Tom (health) and Andy (transport) will follow shortly. These will be used as baseline for the plan but also selections from them will be used for presentations to the public. Information is useful but in some cases incomplete or outdated: however it is the best available. Adrian and John had also included summaries of policies and other information from the DCS….
5. Parish and ward data: much of the statistical information we have is for Alvechurch Ward (i.e. ward of the parliamentary constituency) rather than the parish – it therefore includes Beoley. Susan pointed out a similar problem at Barnt Green. It was agreed that we proceed in collecting the best information possible but may not always be able to isolate the parish.

6. SHLAA: Adrian circulated the Alvechurch data from the SHLAA, the document which shows areas where development for housing is possible. He noted that BDC emphasise that this does not necessarily mean these sites would be given permission. Susan reminded us there was a new version of the SHLAA. In Alvechurch there are 9 potential sites (two already under discussion as ADRs) plus 6 “discounted” ones. Most are in Alvechurch village. More potential sites can come at any time. It was agreed to mark these up on a map and use them in future consultations with parishioners.
7. Duty to co-operate: A map of potential areas for Redditch expansion was circulated. This has been considered for some years – and rejected - but is now being discussed again. CPRE has proposed to BDC that they complete their Core Strategy without finalising the Redditch co-operation, and treat this as a separate local area plan. 
8. Further presentations: 
For Rowney Green (12 Oct, 8.15): Agreed that the SHLAA not very relevant here.  Adrian to co-ordinate display material. Mary to send a reduced version of the environmental data and questions about housing from earlier paper. Others to send simple sheets for display. Adrian to do poster. Linda to look at compiling main data into simpler form. 

Alvechurch: SHLAA material may form bigger part of display. Sally to send Adrian preferred dates for Lounge on a Saturday in November.

Hopwood: Adrian to find a Saturday in November.

The latter two would be whole-morning sessions with a display and members of the SG taking turns to be present. 
There was no further business and the meeting closed at 12.00
Date of next meeting: October 18thth 2012   10 am. Hopwood Community Centre.

In between: working party group to sort out maps and data – Adrian to circulate.

Both these meetings expected to be on practical detail.





