Minutes No.21: Alvechurch Parish Neighbourhood 

Plan Steering Group Meeting 

Date:

Wednesday 16th October 2013
Venue:
Hopwood Community Hall 10.00 am.

[image: image1.jpg]Alvechurch Parish

neighbourhood plan



Present: Adrian Smith, Mary Green, Linda Allen, Dorothy Snaddon, Steve Lewis, Patrick Riley, Andy Humphries, Mike Dunphy, Tom Thurrell (for last part of meeting)

Apologies: John Cypher

1. The minutes of the last meeting were agreed with one minor alteration of names. There were no matters arising.

2. Consulting special groups: the next step is to finish the first round of consultation by listening to local stakeholders: businesses, landowners and services. Adrian agreed to put an advertisement in the Village in December asking people to contribute, either as individuals or via a short drop-in meeting one evening in January. A press release will go out then to other papers. Andy agreed to write to the governors and head of the local school asking for a slot at a governors’ meeting. Mary agreed to write to the Practice Manager at the surgery. A leaflet will be distributed to local shops and at Bordesley Hall. Mike advised us against contacting local landowners or businesses individually as it might be inequitable.
3. It was agreed that Adrian should put the circulated general advertisement in for the November Village, with an added few words about the District Plan, and a larger logo.

4. Mike advised that we did not need at present to do further consultation with statutory bodies. The full scoping report can be sent with the draft plan when we have one

5. BDC Draft Local Plan representation version: The points where Neighbourhood Plans were important in the Plan were noted, especially in carrying out the green belt review. Mike confirmed that the review would be based on what was needed and most sustainable, rather than a numerical allocation. Our NP can be used to suggest areas of green belt which might be used. Mike said he expected the Plan to be adopted in about a year’s time with the review starting immediately.

6. Next steps and timescale.

November 2013: Advert in Village magazine.

Meeting with consultant to begin drawing up policies: Adrian to arrange meeting
Decide if we will take a criteria-based or site-based approach, using SHLAA
Submit advert focused on Stakeholders in Village, organise leafleting and press release to local papers

December 2013:.
Advert focused in Village, leafleting and press release to local papers

Further work on draft policies and associated SA, with help from consultant
January 2014 Consultation session with stakeholders.
Further work on draft plan, with help from consultant

February 2014: Finalise first draft, with help from consultant

Advertising for consultative event in March

March 2014: Major consultation for Parish: event, questionnaire, on-line etc. Should take the form of “these are the issues we found from you, now here are our policies for the future”
April-May 2014: Revise Plan and produce final draft

June – August 2014: Check all other documentation: SA, Baseline, Consultation statement
Early September 2014: Publish final draft. 6 weeks consultation. Send with Scoping Report to statutory consultees.
October 2014: Revise and submit Plan.

7. Updating evidence base and any other supplementary documents: Mike said we should use the BDC evidence base. Linda agreed to look at updated data. Mike advised us not to try to get parish or even ward level data for housing need as it is not robust or useful. The SA should be prepared as we develop policies.
The meting ended at 11.30

Date of next meeting: Core steering group with Alex Munro, longer session to be arranged 
Next full Steering Group meeting: Wednesday 18 December
