Agenda No.12: Alvechurch Parish Neighbourhood 

Plan Steering Group Meeting 

Date:

Thursday November 15th 2012
Venue:
Hopwood Community Hall 10 am.

[image: image1.jpg]Alvechurch Parish

neighbourhood plan



Present: Adrian Smith, Mary Green, Linda Allen, Andy Humphries, Tom Thurrell, Susan Whitehand (BGPC)
Apologies: John Cypher, Mike Dunphy
1. The minutes of the meeting of 18 October were agreed and signed
2. Next year’s budget: We have asked the PC for £500 to cover next year. Currently we have £222.71. We are operating on the time and goodwill of members of the steering group, and do not feel we can commit the PC to bigger expenditure, for example for consultants. 
3. CPRE training 27 & 28 Nov: CPRE have not yet firmed up on timing. It was agreed that we remind them we had no feedback on tasks set last time, and we should insist on better feedback this time if they set us tasks to do. Susan was advised to press on with getting their own CPRE session as ours would be customised to us at this stage.
4. Notification for web site regarding BDC publication of designated area: Mike Dunphy has informed us that notification has gone through Cabinet and will appear shortly on the BDC website. Mike will send Adrian the wording to go on our website (PC and NP sites). It was agreed that we gather information from a counter on the pages, and that Adrian does a short one-paragraph item for the Village magazine directing people to the website.
5. Preparations for the Lounge Drop in event on 17th Nov 2012:

The following arrangements were checked and confirmed:
Adrian has produced the table sheets, 60 questionnaires, posters (already up), laptop rolling background information. Adrian, Mary and John to bring laptops with the PP presentation on. 

Adrian has pens, stickers etc to bring

Noticeboards to have the maps as before, but an explanatory heading needed on the SHLAA one. Material to be kept simple with prominent logos and website.

Adrian will put cover with logo on suggestion box.

Mary will bring contact book. 

All café users to be approached and invited to contribute by writing/sticking on table sheets, or filling in questionnaires, or putting longer comments in post box. Non Parish residents to be asked to note their involvement in the Parish (work here, use school, shop here etc)

Internet on Lounge computers to be set to APNP website

If possible, questionnaires to be taken to businesses around centre

Rota: MG and AS to be there from 9. JC (with laptop) by 11, LA by 12. MG will leave at 12. AH and TT gave apologies.

6. Moving forward: Mary will analyse the returned questionnaires. Adrian will take questionnaires to Weatheroak Residents Association. Sessions to be arranged at Hopwood and Alvechurch VH for new year.
Date of next meeting
20thth Dec 2012   10 am. Hopwood C/Hall
The meeting ended at 11.45  
